## Product Backlog
Product Name: | Robot Shop
Team ID:
Name: | Mary
Initials: | MH
Student ID: | 1001244019
(Additional names for teams only)
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Name:
Initials:
Student ID:
Total Features | 4
Sprint 1 Left | 3
Sprint 2 Left | 3
Sprint 3 Left | 3
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID | Prio | Status | Sprint # | As a... | I want to... | So that... | Notes
RP | 1 | Done | 1 | PM | create robot parts | I can define robot models | No menu required here – run program, create a part
| 2 | NS | 2 | PM | define new robot models | RRS can sell them to our Beloved Customers | Menu needed – create parts, then create a robot model
| 3 | NS | 2 | BC | browse a catalog of robots | I can buy one or more robots | Need to list robots models, then list parts in selected model
| 4 | NS | 3 | SA | create a robot order for a Customer | I can sell robots and thus do my job well | Select robot model and quantity, show details with total price
| 5 |  |  | PB | ensure persistence of the RRS data | we don't lose orders or historical data | Write the data to disk and reload it next time the program runs
| 6 |  |  | PB / SA | view a list of orders per SA | I can estimate the value of employees / I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
| 7 |  |  | BC | view my orders | see what I have coming to me | Show list of orders for a BC with total price, then list details of selected order
| 8 |  |  | BC | view my bill | I can pay for my robots | Show a BC invoice. Actual payment is outside the scope of this project
| 9 |  |  | SA | view a sales report | I can justify a raise | Show list of orders for an SA with total price, then list details of selected order
| 10 |  |  | PB | view a list of orders | I can manage the company | Show list of every order with total price, then list details of selected order
| 11 |  |  | SA | create a bulk (2+) robot order for a Customer | avoid proliferation of orders and paperwork | Allow more than one robot model (with respective quantity) on a single order
| 12 |  |  | PM | hide robot parts | obsolete parts aren't accidentally used | Mark robot parts as “obsolete” and don't allow adding them to new robot models
| 13 |  |  | PM | hide robot models | obsolete robots aren't ordered | Mark robot models as “obsolete” and don't allow adding them to new orders
| 14 |  |  | SA | save a draft order and return to it later | I can multi-task between indecisive customers | Save an order that hasn't been complete, and allow SA to resume work on it later
| 15 |  |  | PM | add custom pictures to robot models | BC are more likely to buy my robots | (Probably can't address until Homework #6)
| 16 |  |  | BC | see a pie chart of a model's component costs | I can decide if I want a different model | (Probably can't address until Homework #6)
| 17 |  |  | BC | browse and order robots over the web | I don't have to talk to the Sales Associates! | (Probably can't address until Homework #6)
| 18 |  |  | PB | avoid any delays in the RRS web software | my SA team is at maximum productivity | This likely means using threads for key processes (Probably can't address until Homework #6)

## Sprint 1 Backlog
Sprint # | 1
Start on | 2016-09-29
End on | 1986-10-01
Demo on | 2016-10-06
Total Tasks | 17
Day 1 Left | 17
Day 2 Left | 17
Day 3 Left | 15
Day 4 Left | 10
Day 5 Left | 6
Day 6 Left | 1
Day 7 Left | 1
Task ID | Feature ID | Category | Type | Assigned To | Description | Status | Notes
1 |  |  |  | MH | Class Diagram
2 |  |  |  | MH | Use Case
3 |  |  |  | MH | Make class for componetType | Done
4 |  |  |  | MH | Test type.h | Done
5 |  |  |  | MH | Make RobotPart.h | Done
6 |  |  |  | MH | Test robotPart (abstract) | Done
7 |  |  |  | MH | Make arm class | Done
8 |  |  |  | MH | Test Arm class | Done
9 |  |  |  | MH | Make Locomotor Class | Done
10 |  |  |  | MH | Test Locomotor Class | Done
11 |  |  |  | MH | Make battery class | Done
12 |  |  |  | MH | Test Battery Class | Done
13 |  |  |  | MH | Make head Class | Done
14 |  |  |  | MH | test head Class | Done
15 |  |  |  | MH | make torso Class | Done
16 |  |  |  | MH | test torso Class | Done
17 |  |  |  | MH | Turn in Sprint